## Sheet1
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
SECURITY
DF_001 | application_network_failure | Website is not asking to enter username and password again after network failure | Detailed Description: Newtours website is not asking to enter username and password again after network failure. Steps To reproduce the bug: 1.Open browser. 2.Enter www.newtours.demoaut.com in the address bar. 3.Enter the username. 4.Enter the password. 5.Click on login button. 6. disconnect the internet connection and reconnect it again. Actual result observed on running above steps: On disconnecting the internet the website is not asking to enter username and password again and is resuming from the stage where internet connection was disconnected. | Coding | Internet explorer | Internal Dev | P1 | High | 1.3.1 | 1899-12-31 | 2018-11-24 | Suraj Singh | Tarang Gupta | ACT |  | TC_001
DF_002 | application_power_failure | Website is not asking to enter username and password again after power failure. | Detailed Description: Newtours website is not asking to enter username and password again after power failure. Steps To reproduce the bug: 1.Open browser. 2.Enter www.newtours.demoaut.com in the address bar. 3.Enter the username. 4.Enter the password. 5.Click on login button. 6. disconnect the power connection and reconnect it again. Actual result observed on running above steps: On disconnecting the power connection the website is not asking to enter username and password again and is resuming from the stage where power connection was disconnected. | Coding | Internet explorer | Internal Dev | P1 | High | 1.3.1 | 1899-12-31 | 2018-11-24 | Suraj Singh | Tarang Gupta | ACT |  | TC_002
DF_003 | application_url_check | Website is unable to hide user login credentials and is showing it in address bar. | Detailed Description: Newtours website is unable to hide user login credentials and is showing it in address bar. Steps To reproduce the bug: 1.Open browser. 2.Enter www.newtours.demoaut.com in the address bar. 3.Enter the username. 4.Enter the password. 5.Click on login button. 6.Check whether or not the username and password is visible in the address bar. Actual result observed on running above steps: On entering the log in credentials and clicking the login button the login credentials is being displayed in address bar. | Coding | Internet explorer | Internal Dev | P1 | High | 1.3.1 | 1899-12-31 | 2018-11-24 | Suraj Singh | Tarang Gupta | ACT |  | TC_003
DF_004 | application_idle_check | Website is not asking to enter log in credentials again when left idle for longer period. | Detailed Description: Newtours website is not asking to enter log in credentials again when left idle for longer period Steps To reproduce the bug: 1.Open browser. 2.Enter www.newtours.demoaut.com in the address bar. 3.Enter the username. 4.Enter the password. 5.Click on login button. 6.Check whether it is asking to enter login credentials again when leftidle for longer period. Actual result observed on running above steps: On leaving website idle for the longer period application is not asking to enter log in credentials again. | Coding | Internet explorer | Internal Dev | P1 | High | 1.3.1 | 1899-12-31 | 2018-11-24 | Suraj Singh | Tarang Gupta | ACT |  | TC_004
DF_005 | application_close | Website is not prompting alert when tried to close it forcefully. | Detailed Description: Newtours website is not prompting alert when tried to close it forcefully. Steps To reproduce the bug: 1.Open browser. 2.Enter www.newtours.demoaut.com in the address bar. 3.Enter the username. 4.Enter the password. 5.Click on login button. 6.Close the application forcefully. Actual result observed on running above steps: On trying to close the application forcefully the application is not showing any alert message "Are you sure you want to exit?" | Coding | Internet explorer | Internal Dev | P1 | High | 1.3.1 | 1899-12-31 | 2018-11-24 | Suraj Singh | Tarang Gupta | ACT |  | TC_005
USE CASE
DF_001 | NewTours_Registration | The webpage is found unable to display error message (This user already registered) when the Registered user is doing the registration | Detailed Description: In website NewTours the webpage is found unable to display error message (This user already registered) when the Registered user is doing the registration Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website and fill Sign-On credentials 3. Click on "Register" link 4. Fill the Register credentials 5. Click on the submit button Actual results observed on running above steps: On executing the above mentioned steps it is observed that the webpage is not displaying the error message "This user already registered" as expected. | Coding | Internet Explorer | Internal Dev | P2 | Medium | 1.3.1 | 2 | 2018-11-02 | Vartika Garg | Tarang Gupta | ACT |  | TC_003
DF_002 | NewTours_Flight Booking | The website is found unable to give access to the Registered user to book the flights | Detailed Description: In website NewTours the website is found unable to give access to the Registered user to book the flights Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website and fill Sign-On credentials 3. Click on "Flights" link 4. Enter the valid credentials in Flight Finder 5. Click in the Continue button 6. Enter the valid credentials in Select Flight 7. Click in the Continue button 8. Enter the valid credentials in Book A Flight 9. Click on the Secure Purchase Actual results observed on running above steps: On executing the above mentioned steps it is observed that the website is unable to give access to the Registered user to book the flights as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 | 2018-11-02 | Vartika Garg | Tarang Gupta | ACT |  | TC_006
DF_003 | NewTours_Flight Booking | The webpage is found unable to display error message (The user should register first) when the Non Registered user is booking the flights | Detailed Description: In website NewTours the webpage is found unable to display error message (The user should register first) when the Non Registered user is booking the flights Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website and fill Sign-On credentials 3. Click on "Flights" link 4. Enter the valid credentials in Flight Finder 5. Click in the Continue button 6. Enter the valid credentials in Select Flight 7. Click in the Continue button 8. Enter the valid credentials in Book A Flight 9. Click on the Secure Purchase Actual results observed on running above steps: On executing the above mentioned steps it is observed that the webpage is not displaying the error message "This user should register first" as expected. | Coding | Internet Explorer | Internal Dev | P2 | Medium | 1.3.1 | 2 | 2018-11-02 | Vartika Garg | Tarang Gupta | ACT |  | TC_007
DF_004 | NewTours_Edit Profile | The webpage is found unable to display error message (Only registered User can edit the profile) when the Non Registered user edits the Profile | Detailed Description: In website NewTours the webpage is found unable to display error message (Only registered User can edit the profile) when the Non Registered user edits the Profile Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website and fill Sign-On credentials 3. Click on "Flights" link 4. Click on "Profile" link Actual results observed on running above steps: On executing the above mentioned steps it is observed that the webpage is not displaying the error message "Only registered User can edit the profile" as expected. | Coding | Internet Explorer | Internal Dev | P2 | Medium | 1.3.1 | 2 | 2018-11-02 | Vartika Garg | Tarang Gupta | ACT |  | TC_008
DF_005 | NewTours_Edit Profile | The website is found unable to give access to the Registered user to edit the Profile | Detailed Description: In website NewTours the website is found unable to give access to the Registered user to edit the Profile Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website and fill Sign-On credentials 3. Click on "Flights" link 4. Click on "Profile" link Actual results observed on running above steps: On executing the above mentioned steps it is observed that the website is found unable to give access to the Registered user to edit the Profile as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 | 2018-11-02 | Vartika Garg | Tarang Gupta | ACT |  | TC_009
STATE TRANSITION
DF_HOME_001 | Sign-On | The "Submit" button on the "Sign-On" page of the Mercury Tours is found unable to navigate the user to the "Successful Login" page. | Detailed Description: The user clicks on the "Submit" button after entering valid username and password. The button is found unable to navigate the user to the web page displaying "Successful Login". Steps To reproduce the bug: 1. Open Browser. 2. Enter URL for the website. 3. Click on the "Sign-On" menu. 4. Enter valid login credentials. 5. Click on "Submit" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate the user to the "Successful Login" page as expected. The page gets refreshed and stays on the same page. | Coding | Internet explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 22/01/2015 | Vaibhav Jagde | Tarang Gupta | ACT |  | TC_002
CAUSE AND EFFECT
DF_001 | Registration | TheEmail Field is found to accept invalid email | Detailed Description: In Registartion Page.The Email Field is found to accept invalid Email Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website. 3. Click on "Registration" link 4. Enter the Email Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Email Field is accepting the invalid Email address.The system does not displays message to type enter valid Email addres again. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 1 | 2018-11-02 | Vishal Vishwakarma | Suraj Singh | ACT |  | TC_001
DF_002 | Registration | The webpage is found unable to display error message(Password and Confirm password missmatch) by accepting different passwords. | Detailed Description: The webpage is found unable to display error message(Password and Confirm password missmatch) by accepting different passwords Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website. 3. Click on "Registration" link 4. Enter The different Passwords in both the fields. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Webpage is not displaying error message(Password and Confirm password missmatch) as expected. The Password and confirm password field is not validated. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 | 2018-11-02 | Vishal Vishwakarma | Suraj Singh | ACT |  | TC_002
DF_003 | Registration | The account is created without setting password. | Detailed Description: The webpage is found unable to display error message(Password and Confirm password field should not be left blank). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website. 3. Fill all the details and keep password and confirm password field blank. 5. Click on the SUBMIT button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that The Account is created successfully and user directed to next page with message displayed account confirmation. | Coding | Internet Explorer | Internal Dev | P2 | High | 1.3.1 | 3 | 2018-11-02 | Vishal Vishwakarma | Suraj Singh | ACT |  | TC_003
DF_004 | Home | User is directed to Sign-In page after Siging in from the Home page. | Detailed Description: User is directed to Sign-In page after clicking on the Sign-In button after entering the Sign_in credentials. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website and fill Sign-In Credentials 3. Click on Sign-In button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the User directed to Sign-In page instaed of Loggin in to the account. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 4 | 2018-11-02 | Vishal Vishwakarma | Suraj Singh | ACT |  | TC_004
DF_005 | Flight booking | The Card number field is unable to validate the data. | Detailed Description: In Flight booking Web Page The Crad number Field is found unable to validate the data. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website and fill Sign - inCredentials 3. Click on "Flight booking" link 4. Enter the details for finding the flight. 5.Choose the flight based on the details. 6.Enter the Passanger details and Credit card details. 7.Click on continue button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Card number Field is accepting alphanumeric characters instead of numeric characters. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.1 | 2 | 2018-11-02 | Vishal Vishwakarma | Suraj Singh | ACT |  | TC_005
Note on A1: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B1: Alphy Chenganiyadan: Give the name of the module being tested
Note on C1: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D1: Alphy Chenganiyadan: A detailed description of the defect
Note on E1: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F1: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G1: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H1: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I1: Prioritize the defect
Note on J1: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K1: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L1: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M1: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N1: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O1: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P1: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q1: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R1: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S1: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T1: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U1: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V1: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W1: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X1: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y1: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.