## Sheet1
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_HOME_001 | Home | The "Submit" button on the "Sign-On" page of the Mercury Tours is found unable to navigate the user to the "Successful Login" page. | Detailed Description: The user clicks on the "Submit" button after entering valid username and password. The button is found unable to navigate the user to the web page displaying "Successful Login". Steps To reproduce the bug: 1. Open Browser. 2. Enter URL for the website. 3. Click on the "Sign-On" menu. 4. Enter valid login credentials. 5. Click on "Submit" button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application unable to navigate the user to the "Successful Login" page as expected. The page gets refreshed and stays on the same page. | Coding | Chrome | Internal Dev | P0 | High | 1.3.4 | 4 | 22/01/2015 | Neelima Padmawar | Rutuja Kulkarni | ACT |  | TC_HOME_002
Note on A1: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B1: Alphy Chenganiyadan: Give the name of the module being tested
Note on C1: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D1: Alphy Chenganiyadan: A detailed description of the defect
Note on E1: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F1: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G1: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H1: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I1: Prioritize the defect
Note on J1: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K1: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L1: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M1: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N1: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O1: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P1: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q1: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R1: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S1: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T1: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U1: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V1: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W1: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X1: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y1: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.